## Guidelines
Project safety !!
Work Area
Chiller Building + Pipe Rack G
Pipe Rack H + Temp Chiller
Pipe Rack K Section
New Compressor Building
New Boiler Building
Evaporator 2.9Mtr
Evaporator 5Mtr
Evaporator 8Mtr
Evaporator 11Mtr
Evaporator 14Mtr
Evaporator Top Roof
Evaporator Cooling Tower Area
Feedline Area (NH3 + N2 + trane Chiller)
Packing Area HCA
Packing Area MCA
RAW CIP
Process CIP
Milk Reception
Milk Process
HSM
Car Parking + Front Lawn
Oil blending
Oil Storage
WWTP
Upcoming STP
Scrap Yard
MWRS Roof
Contractor Yard

## GEA
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
GEA | 15-06-2026 | Day | A&B | 1. Grid C, joined pieces full welding work. 2. Grid C, Platform pieces lifting and installltion work. 3.Grid C, Leg installation work. 4. Landing platform for 8.1 meter and 5.4 meter shifting from admin to evaporator area. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 25 | Vinoth S | Surender J / Manoj K
GEA | 16-06-2026 | Day | A&B | 1. Scaffolding erection at 2.9 meter platform for chain pully installation. (also inculdes the scaffolding material shifting at 2.9meter platform). 2. Chain pully block shifting from grid C and installation (at +10.96M) in grid-A as well as GRID-C (for Platform lifting) at +14.86M. 3. Temp. Base structure to be fabricated at 2.9 meter platform. (to support and alignment or joint of two platform pieces). | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 25 | Vinoth S | Surender J / Manoj K
GEA | 17-06-2026 | Day | A&B | 11. Base plate installation or anchoring (includes drilling & chemical filling). For 8.1 meter landing platform. 2. Platform Lifting and installation work for 8.1 Mtr. 3. Material Unloading and shifting work for platforms. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S | Surender J / Manoj K
GEA | 18-06-2026 | Day | A&B | 1. Base plate installation or anchoring (includes drilling & chemical filling). For 5.4 meter landing platform. 2. Platform lifting and shifting work for 5.4 mtr. Landing platform. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S | Surender J / Manoj K
GEA | 19-06-2026 | Day | A&B | 1. Platform lifting and shifting work for 5.4 mtr. Landing platform with welding work. 2. Platform lifting and shifting work from storage area to evaporator building. 3. Platform lifting and shifting inside evaporator building. Chain pully blocks installation work. 4. Material unloading and shifting work. 5. Base plate installation or anchoring (includes drilling & chemical filling). This activities includes scafolding erection and dismantling work. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S | Surender J / Manoj K
GEA | 20-06-2026 | Day | A&B | 1. Base plate installation or anchoring (includes drilling & chemical filling). This activities includes scafolding erection and dismantling work. 2. Platform lifting and shifting work from storage area to evaporator building. 3. Platform lifting and shifting inside evaporator building. Chain pully blocks installation work. 4. Full welding work for platform structure. 5. Staircase installation work for 5.4 mtr. and 8.1 mtr landing platforms. 6. Material unloading and shifting work. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S | Surender J / Manoj K
GEA | 22-06-2026 | Day | A&B | 1. Base plate installation or anchoring (includes drilling & chemical filling). This activities includes scafolding erection and dismantling work. 2. Platform lifting and shifting work from storage area to evaporator building. 3. Platform lifting and shifting inside evaporator building. Chain pully blocks installation work. 4. Full welding work for platform structure. 5. Staircase installation work for 5.4 mtr. and 8.1 mtr landing platforms. Along with railing work for staircase of 2.9, 5.4 & 8.1 mtr landing platforms 6. Material unloading and shifting work. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 23-06-2026 | Day | A&B | 1. Railing work for staircase of 2.9, 5.4 & 8.1 mtr landing platforms. 2. Platform Lifting and installation work inside evaporator building. Chain pully blocks installation work. 3. Welding work for Platform structure. 4. Scafolding erection and dismantling work inside evaporator building. 5. Material unloading and shifting work. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 24-06-2026 | Day | A&B | 1. Platform 8.1 meter Section - B Fittup, Installation and welding work. 2. Platform shifting from admin to evap. Building (for 2.9 meter, section C.1) | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 25-06-2026 | Day | A&B | 1. Platform 8.1 meter, Section - B lifting, installation & welding work. 2. 2.9 meter platform cutting and fabrication work. Also shifting from outside to inside evaporator building. 3. Structure fabrication work at 8.1 meter platform (in section A&B). | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 26-06-2026 | Day | A&B | 1. 2.9 meter platform (In section C-1) lifting, installation and welding work. 2. Base plate drilling and fixing for 10.9 meter landing platform (in section A). | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 26-06-2026 | Night | C&D | 1. Full welding work for 2.9 meter platform (in section C-1). 2. Base plate drilling and fixing for 10.9 meter platform (in section A & B). | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30 | Vinoth S / S.Jaspal | Yes
GEA | 27-06-2026 | Day | A&B | 1. Base plates drilling and fixing for 8.1 meter platform in section C-1. 2. 10.9 meter landing platform lifting and shifting from 0 meter to top of 8.1 meter platform . | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 27-06-2026 | Night | C&D | 1. Lifting and installation of 10.9 meter landing platform in section A. 2. Base plate drilling and fixing for 10.9 meter landing platform (in section B). | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 29-06-2026 | Day | A&B | 1. Platform 8.1 meter in Section C-1, lifting and shifting from 0 meter to "at 2.9 meter platform". 2. Lifting and installation of 10.9 meter platform in section A, with welding work. 3. Staircase shifting from admin to inside evaporator and from zero meter to "at 8.1 meter platform". | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 29-06-2026 | Night | C&D | 1. Base plate drilling and fixing for 10.9 meter landing platform (in section B). 2. Full welding work for landing platform at 10.9 meter in section A. 3. Installation work for staircase from 8.1 to 10.9 meter platforms in section A. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 30-06-2026 | Day | A&B | 1. Platform for 8.1 meter in section C-1, installation and welding work. 2. 10.9 meter platform shifting from admin to inside evaporator building. 03 pieces out of 04 will be shifted | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 30-06-2026 | Night | C&D | 1. Platform for 8.1 meter in section C-1, full welding work. 2. 10.9 Meter platform (for section B) pieces cutting and fabrication work. 3. 10.9 platform (for section B) pieces will be lifted and shifted from zero meter to "at 8.1 meter platform" and in section B. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-01 | Day | A&B | 1. Base plate drilling and fixning in 10.9 section B. 2. Platform shifting from admin to evaporator section and shifting and lifting inside evaporator from 0 meter to "at 8.1 meter platform". 3. Welding work for 10.9 meter landing platform. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-01 | Night | C&D | 1. Base plate drilling and fixning in 10.9 section B. 2. Platform shifting and lifting inside evaporator from 0 meter to "at 8.1 meter platform". Platform pieces joint together which includes cutting and welding work. 3. Welding work for 10.9 meter landing platform. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-02 | Day | A&B | 1. 10.9 meter platform Section B, joint of pieces and welding. Lifting and installation for the same. 2. 10.9 meter, section b, Base plate drilling and fixing. 3. 10.9 meter platform in section b, Full welding work. 4. Lifting and shifting of 14.8 meter landing platform from admin to evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-02 | Night | C&D | 1. 10.9 meter platform Section B, joint of pieces and welding. Lifting and installation for the same. 2. 10.9 meter, section b, Base plate drilling and fixing. 3. 10.9 meter platform in section b, Full welding work. 4. Lifting and shifting of 14.8 meter landing platform from admin to evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-03 | Day | A&B | 1. Full welding of 10.9 meter platform in section B. 2. Cutting, shifting and lifting of 14.8 meter landing platform from 0 meter to "at 10.9 meter platform". 3. Cutting, Lifting and shifting of 10.9 meter platform pieces (for section C-1 & 2) from admin to evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-03 | Night | C&D | 1. Drilling and fixing and chemical filling work for base plates in 8.1 meter section C-1. 2. Cutting, shifting and lifting of 14.8 meter landing platform from 0 meter to "at 10.9 meter platform". 3. Cutting, Lifting and shifting of 10.9 meter platform pieces (for section C-1 & 2) from admin to evaporator building. 4. Full welding of 10.9 meter platform in section B. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-04 | Day | A&B | 1. Cutting, Lifting and shifting of 10.9 meter platform for section C-1 & 2, from 0 meter to "at 8.1 meter platform" Plform pieces will be kept at 8.1 meter insection B. 2. Plaform pieces for 8.1 meter section C-1 & 2, shifting and lifting from admin to evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-04 | Night | C&D | 1. Joint of all platform pieces for 10.9 section C-1 & 2. welding work for the same. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-06 | Day | A&B | 1. Plaform pieces for 8.1 meter section C-1 & 2, shifting and lifting from admin to evaporator building. 2. supporting structure fabrication work at 2.9 meter platform into section B. 3. Staircase for 8.1 to 10 meter platforms will be shifted in evaporator building.' | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-06 | Night | C&D | 1. supporting structure fabrication work at 2.9 meter platform into section B. 2. Platform pieces cutting inside evaporator building. Plaform for 8.1 meter section C-1 & 2 which was shifted in day shift. 3. Staircase for 8.1 to 10 meter platforms will be Lifting, shifted and installation work in evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-07 | Day | A&B | 1. Platform pieces for 8.1 meter section C, will be lifted and shifted from 0 meter to "at 2.9 meter platform in section B". 2. Platform pieces for 8.1 meter section C, which kept at 2.9 meter section B, will be joint together with weling work. 3. Staircase and small landing platform in between 10.9 to 14.8 meter, lifting and shifting work from zero meter to "at 10.9 meter in section A" | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-07 | Night | C&D | 1. Platform pieces for 8.1 meter section C, will be lifted and shifted from 0 meter to "at 2.9 meter platform in section B". 2. Platform pieces for 8.1 meter section C, which kept at 2.9 meter section B, will be joint together with welding work. 3. Staircase and small landing platform in between 10.9 to 14.8 meter, lifting and shifting work from zero meter to "at 10.9 meter in section A" | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-08 | Day | A&B | 1. welding work for 8.1 meter platform sectionn C-1 & 2. 2. Drilling, base plate fixing and chemical filling work for 2.9 meter platform in section C-2. 3. Lifting and shifting work for 2.9 meter platform section C-2, from admin to evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-08 | Night | C&D | 1. Drilling, base plate fixing and chemical filling work for 2.9 meter platform in section C-2. 2. 2.9 meter platform section C-2, cutting and joint together inside evaporator building. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-09 | Day | A&B | 1. Base structure fabrication for platform at zero meter in section C-2. 2. Full welding work for platform joint pieces of 2.9 meter section C-2. 3. Platform lifting and installation work for 2.9 meter section C-2. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-09 | Night | C&D | 1. Platform lifting and installation work for 2.9 meter section C-2. and welding work for the same. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-10 | Day | A&B | 1. Platform welding work for 2.9 meter section C-2. 2. Drilling, base plate fixing and chemical filling work for 8.1 meter platform in section C-2. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-10 | Night | C&D | 1. Base structure fabrication for platform at 2.9 meter in section C-2. 2. Drilling, base plate fixing and chemical filling work for 8.1 meter platform in section C-2. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-11 | Day | A&B | 1. Platform lifting and installation work for 8.1 meter section C-1 & 2. and welding work for the same. 2. Base structure dismantling from zero meter and installation at 10.9 meter platform in section A & B. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-11 | Night | C&D | 1. Full welding work for 8.1 meter platform section C-1 & 2. 2. Base structure dismantling from zero meter and installation at 10.9 meter platform in section A & B. | 1) General Work 2) Hot work 3) Height Work 4) Heavy Lifting | Evaporator 2.9Mtr | Hot Work, Heavy Lifting Work | Yes | Yes | 1. Bijay Kumar 2. Sandeep Rai | 1. Nitin 2. Balram | 30
GEA | 2026-07-12 | Day
GEA | 2026-07-12 | Night
GEA | 2026-07-13 | Day
GEA | 2026-07-13 | Night
GEA | 2026-07-14 | Day
GEA | 2026-07-14 | Night
GEA | 2026-07-15 | Day
GEA | 2026-07-15 | Night
GEA | 2026-07-16 | Day
GEA | 2026-07-16 | Night
GEA | 2026-07-17 | Day
GEA | 2026-07-17 | Night
GEA | 2026-07-18 | Day
GEA | 2026-07-18 | Night

## SPX Flo
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
SPX | 2026-06-14 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-15 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-16 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-17 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-18 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-19 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-20 | Day | A & B | 1) Insulation Work 2) Cladding Work 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Akshay | Yes
SPX | 2026-06-21 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-22 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-23 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-24 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-25 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-26 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-27 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-28 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-29 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-06-30 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-01 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-02 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-03 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-04 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. | Hot Work/ Height Work/ Shifting work/General Work | Oil Blending To Oil Reception Area | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-05 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-06 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-07 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-08 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-09 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-10 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes
SPX | 2026-07-11 | Day | A & B | 1) Insulation Work ( From DG Room to Oil reception ) 2) Cladding Work ( From DG Room to Oil reception) 3) Welding Work for Minor modification Work. 4) Platform Fabrication & Installation For Mix Proof valve Installation. 5) PHE & Pump Material Unloading & Installation 6) Manual Material Handling 7) Fabrication Work at Height | Hot Work/ Height Work/ Shifting work/General Work/ Confined Space Work | Oil Blending To Oil Reception Area / Gate No 02 | 1) Scaffolding dismantling & erection.. 2) Fabrication Work at Ground & height 3) Confined Space Work | Yes | YES | Pushp | Aftab |  | Tajinder Mavi Akshay | Yes

## Fluidline
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
Fluidline | 2026-06-14 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-14 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-15 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-15 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-15 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-16 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-16 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-16 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-17 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-17 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-17 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-18 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-18 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-18 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-19 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-19 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-19 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-20 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes |  |  |  | Akshay | Yes | 07:00 am To 07:00 pm
Fluidline | 2026-06-20 | Day | A/B | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift 3) Pipe Line laying Work From G to H Pipe Rack 4) Welding work.at ground & height 5) Material Shifting. 6) Welding Work with Boom Lift | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes |  |  |  | Akshay | Yes | 09:00 am To 09:00 pm
Fluidline | 2026-06-20 | Night | B/C | 1) Ammonia Recovery Work 2) Pipe Fabrication Work 3) Tank Lifting & Shifting Work 4) Nitrogen system Dismantling Work 5) Air Compressor Dismantling Work 6) PHE & Mezzanine Floor Dismantling Work | Hot Work/ Height Work/Lifting work/General Work | Refrigeration room | 1) Transfer of Ammonia From Exiting Setup to new receiver tank 2) Fabrication ground & height job. 3) Material shifting with Farana and With HOPT 4) Nitrogen tank Lifting with Chain pulley | Yes | Yes |  |  |  | Akshay | Yes | 09:00 AM To 06:00PM - 1st Shift 06:00 PM to 02:00 AM -2nd Shift Note : Ammonia dismantling work is linked with the chiller commissioning work. Once we complete the commissioning, we will proceed with ammonia dismantling. In this case, we will communicate with you and the other vendors 3 days in advance to execute the work.
Fluidline | 2026-06-21 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-22 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-23 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-24 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-25 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-26 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-27 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-28 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-29 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-06-30 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-07-01 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-07-02 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-07-03 | Day/ Night | G/A/B | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-07-04 | Day/ Night | G/A/B | l | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Akshay | Yes
Fluidline | 2026-07-05 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-06 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-07 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-08 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-09 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-10 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
Fluidline | 2026-07-11 | Day/ Night | G/A/B/C | 1) Scaffoding dismantling & Erection work. 2) Pump & Cooling tower Positioning 3) PHE shifting & Positioning. 4) Material Shifting ; Piping , Pump From Admin to New Chiller. 5) Cooling Tower Installation Work. | Hot Work/ Height Work/Lifting work/General Work | New Chiller Area | 1) Scaffolding dismantling & erection.. 2) Hot Work & height Work 3) Heavy lifting, Material shifting & lifting with Farana and manual. 5) Cooling Tower Installation Work at chiller roof. | Yes | Yes | Balwant / Dheeraj | Ashwani / Prabraj / Madhav | 60 | Ajay / Akshay | Yes
|  |  |  | 1) Scaffoding dismantling & Erection work. 2) Height & Hot Work with Boom Lift for Pipe Line 3) Pipe Line laying Work From G to H Pipe Rack using farana 4) Welding work.at ground & height 5) Material Shifting ( Manually + Mechanically ) 6) Welding Work with Boom Lift 7) Insulation Work | Hot Work/ Height Work/Lifting work/General Work | Outside & Backside MWRS Area / Canteen Outside | 1) Scaffolding dismantling & erection.. 2) Hot Work at Pipe rack using boom lift. 3) Material shifting with Farana and manual. 4) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes
|  |  |  | 1) Raw water line laying Work ( From K Pipe Rack to G Pipe rack) 2) Height Work & Hot Work with boom lift 3) Scaffoding dismantling & Erection work. | Hot Work/ Height Work/Lifting work/General Work | Refrigeration Terrace to New Chiller Area | 1) Hot Work at Pipe rack using boom lift. 2) Material shifting with Farana and manual. 3) Pipe Line laying Work From G to H Pipe Rack using farana. | Yes | Yes | Puspinder/ Narinder | Ashwani / Prabraj / Madhav |  | Ajay / Akshay | Yes

## Satnam (hidden)
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Renucore
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
Renucore | 2026-06-14 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-14 | Day | G | 1) Wall Demolition Work 2) Duct modification Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work | General Work/Hot work/ Height Work | Refregeration Room / Canteen Area / Project Area | 1) Wall demolition work | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-15 | Night | Monday | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Vinoth S | Surender J / Manoj K | 21:00 to 9:00
Renucore | 2026-06-15 | Day | G | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 09:00 to 21:00
Renucore | 2026-06-15 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-15 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-15 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-16 | Day | A/B | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS |  |  | 09:00 to 21:00
Renucore | 2026-06-16 | Night | C | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS |  |  | 21:00 to 09:00
Renucore | 2026-06-16 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-16 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-16 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-17 | Day | A/B | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 09:00 to 21:00
Renucore | 2026-06-17 | Night | C | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 21:00 to 09:00
Renucore | 2026-06-17 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-17 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-17 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-18 | Day | A/B | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 09:00 to 21:00
Renucore | 2026-06-18 | Night | C | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 21:00 to 09:00
Renucore | 2026-06-18 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-18 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-18 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-19 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-19 | Day | A/B | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 09:00 to 21:00
Renucore | 2026-06-19 | Night | C | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 21:00 to 09:00
Renucore | 2026-06-19 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-19 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-20 | Day | G | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-20 | Day | G | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-20 | Day | G | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA |  |  |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-20 | Day | A/B | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 09:00 to 21:00
Renucore | 2026-06-20 | Night | C | 1) Wall Construction Work 2) Tilie Fixing Work 3) Puf Panel Fixing Work 4) Sheet removing & Fixing Work 5) Plaster Paint Putty Work 6) Material shifting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh | 2 MASON+2 HELPERS | Surenedr | Yes | 21:00 to 09:00
Renucore | 2026-06-21 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-22 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-23 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-24 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-25 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-26 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-27 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
Renucore | 2026-06-27 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-27 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-28 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-29 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-06-30 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-01 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-02 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-03 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-04 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting 4) Grating Fabrication Installation Work | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Lifeline Installation Work 2) Sacffolding Errection & Dismantling Work 3) Tarfelt Laying Work 4) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-05 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-06 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-07 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-08 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-09 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-10 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00
Renucore | 2026-07-11 | Day | G/B | 1) Painting 2) Epoxy flooring & Coving 3) Material shifting | General Work/Hot work | Oil Blending / Oil Reception |  | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Shanawaz | Yes | 9:00 to 6:00
|  |  |  | 1) Sacffolding Errection & Dismantling Work 2) Tarfelt Laying Work 3) Material Shifting Work | General Work/Hot work/ Height Work | Project Office | 1) Lifeline Installation Work at project office roof using boom lift. 2) Scaffolding Erection & Dismantling Work 3) Tarfelt Laying Work at project office roof | Yes | Yes | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Ajay | Yes | 9:00 to 6:00
|  |  |  | 1) Store Racks Dismantling Work 2) Material Shifting Work 3) Cuting Work 4) Heavy material Unloading with chain pulley | General Work / Hot work | Engineering Store | 1) Cutting work 2) Material shifting | Yes | NA | Manuu Yadav Shahid Rohit | Sahil Rishabh |  | Akshay | Yes | 9:00 to 6:00

## Crescon
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
Crescon | 2026-06-14 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-15 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-15 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-16 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-16 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-17 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-17 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-18 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-18 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-19 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-19 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-20 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-20 | Day | A/B | 1. Cooling Tower Frame Lifting & Shifting Work 2. Frame Installation Work. | Genaral, Lifting, Hot work & Height | New Chiller Area | 1) Cooling tower Frame Lifting & shifting using farana | Yes | Yes |  |  |  | Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-21 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-22 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-23 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-24 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-25 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-26 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-27 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-28 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-29 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-06-30 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-01 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-02 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-03 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-04 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-05 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-06 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-07 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-08 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-09 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-10 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm
Crescon | 2026-07-11 | Day | A/B | 1. Material unloading of pipe rack using Farana. 2. Lifting of columns and bracings using Farana. 3. Pipe rack installation work for Pipe Rack F. 4. Bolt and nut tightening using boom lift at Pipe Rack G & H. 5. Grouting work for Pipe Rack G & H. 6. Height work using boom lift for pipe rack alignment. | Genaral, Lifting, Hot work & Height | Refrigeration Building, Canteen Area & MWRS Area | 1)Pipe rack material unloading & Installations using Farana 2)Height work using boom lift for pipe rack alignment. | Yes | Yes | Manni | Pintu / Vishal |  | Akshay Tajinder | Yes | 07:00 am to 07:00 pm

## ESS PEE
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
Ess Pee | 2026-06-15 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-15 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-16 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-16 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-17 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-17 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-18 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-18 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling 6)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-19 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-19 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling 6)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-20 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting using farana 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | surender | Yes | 09:00 to 18:00
Ess Pee | 2026-06-20 | Night | B/C | 1) Piperack Support welding 2) Pipeline welding 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) 5) Scaffolding erection and dismantling 6)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | surender | Yes | 18:00 to 06:00
Ess Pee | 2026-06-21 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-21 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-22 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-22 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-23 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-23 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-24 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-24 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-25 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-25 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-26 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-26 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-27 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-27 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-28 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-28 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-29 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-29 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-06-30 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-06-30 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-07-01 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) ETP pipeline dismantling and rerouting | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-07-01 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-07-02 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) ETP pipeline dismantling and rerouting | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-07-02 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-07-03 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) ETP pipeline dismantling and rerouting | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-07-03 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-07-04 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-07-04 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00
Ess Pee | 2026-07-05 | Day | G | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Material shifting manually and with farana(mobile crane) 6) Scaffolding erection and dismantling 7)Emergency Staircase and platform modification 8) Puff Panel dismantling 9) Existing raw water pipe dismantling and shifting 10) MISC | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Lifting shifting 2) Scaffolding erection" | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender/Vinoth | Yes | 09:00 to 18:00
Ess Pee | 2026-07-05 | Night | B/C | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Material shifting manually and with farana(mobile crane) | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area |  | Yes | Yes | Priyanshu Kumar | Hariom Kumar | 6 | Surender/Vinoth | Yes | 18:00 to 06:00

## Aalanna
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
Aalanna | 2026-06-15 | Day | G/B | 1) Mechanical Excavation Behind FO yard for ETP Tank 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Excavation Work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kumar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-15 | Night | C | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
Aalanna | 2026-06-16 | Day | G/B | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kutar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-16 | Night | C | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
Aalanna | 2026-06-17 | Day | G/B | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kuwar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-17 | Night | C | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting and Core Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
Aalanna | 2026-06-18 | Day | G/B | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kutar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-18 | Night | C | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
Aalanna | 2026-06-19 | Day | G/B | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kufar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-19 | Night | C | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting and Core Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
Aalanna | 2026-06-20 | Day | G/B | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1)Mechanical Excavation Behind FO yard for ETP Tank 2) Soil shifting | No | No | Khalid Hussain | Nitesh Kusar | 9 | Surender |  | 09:00 to 20:00
Aalanna | 2026-06-20 | Night | C | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Scaffolding Erection & Dismantling Work 2) Slab chipping & steel cutting at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-22 | Day | Monday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Excavation Work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kumar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-22 |  |  | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-23 | Day | Tuesday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kusar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-23 |  |  | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-24 | Day | Wednesday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kumar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-24 |  |  | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting and Core Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-25 | Day | Thursday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kusar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-25 |  |  | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-26 | Day | Friday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kumar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-26 |  |  | 1) Slab Chipping 2) Scaffolding Erection and Dismentalling 3) Material shifting 4) Steel Cutting and Core Cutting | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-27 | Day | Saturday | 1) Excavation 2) Sides Slope Shoring 3) Excavated Soil Shifting | 1) General Work 2) Hot work 3) Height Work | ETP Tank | 1) Civil Work 3) Excavation Work | Yes | Yes | Khalid Hussain | Nitesh Kusar | 9 | Surender |  | 09:00 to 20:00
| 2026-06-27 |  |  | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-28 |  | Sunday | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | 20:00 to 06:00
| 2026-06-28 |  | Sunday | 1) Gate no.2 tank excavation work | 1) General Work 2) Excavation | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Worok | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Gaurav chopra |  | 20:00 to 06:00
| 2026-06-29 |  | Monday | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab 3.Eva area chipping work | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | Day/night
| 2026-06-29 |  | Monday | 1) Gate no.2 tank excavation work | 1) General Work 2) Excavation | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Worok | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Gaurav chopra |  | Day/night
| 2026-06-30 |  | Tuesday | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab 3.Eva area chipping work | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | Day/night
| 2026-06-30 |  | Tuesday | 1) Gate no.2 tank excavation work | 1) General Work 2) Excavation | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Worok | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Gaurav chopra |  | Day/night
| 2026-07-01 |  | Wednesday | 1) Tarrece Brickbats Chipping 2) Debries Shifting At Adjacent Slab from Tank Slab 3.Eva area chipping work | 1) General Work 2) Hot work 3) Height Work | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Work 3) Work at Height | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Surender |  | Day/night
| 2026-07-01 |  | Wednesday | 1) Gate no.2 tank excavation work | 1) General Work 2) Excavation | Evaporator area | 1) Civil Work 2) Scaffolding Erection & Dismantling Worok | Yes | Yes | Geyasuddin | Kadir Hussain | 9 | Gaurav chopra |  | Day/night

## Tetrapak
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Devansh
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Ess Win
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Esswin | 2026-07-06 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Esswin | 2026-07-07 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Esswin | 2026-07-08 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Esswin | 2026-07-09 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Esswin | 2026-07-10 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Oil Storage
Esswin | 2026-07-11 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building 5) Cable laying from Oil reveption to New Piperack | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Oil Storage
Esswin | 2026-07-12 | Day | A/B | 1) Cable tray shifting & Installation at Rack & PCC room area 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack 4) Cable laying 300 sq.mm (DG room to New chiller building 5) Cable laying from Oil reception to New Piperack | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting | Chiller Building + Pipe Rack G | Work at height (>10M) using boom lift, hot work (welding), material lifting manually, cable shifting from yard to Piperack all section areas | Yes | Yes | Bhupendra/Irfan | Vikas | 14 | xx | xx | DG Room area need to mentioned in the loaction where the work is to be carried out
Pipe Rack H + Temp Chiller
Pipe Rack K Section
Oil Storage

## TSF
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Sai Electro
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## York JCI
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Forbes
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX

## Crescon civil
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Crescon | 2026-06-15 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-16 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-17 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-18 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-19 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-20 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-21 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-22 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-23 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-24 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-25 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-26 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush | Pintu/dahnuu | 20 | Sahnawaz | yes
Crescon | 2026-06-27 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-06-28 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-06-29 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-06-30 | Day | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-06-30 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-01 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-02 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-03 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-04 | Day/night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-05 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-06 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-07 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | 2026-07-08 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | Thursday, July 9, 2026 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | Friday, July 10, 2026 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | Saturday, July 11, 2026 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes
Crescon | Sunday, July 12, 2026 | Day/Night | A/B/C/G | Chiller building/air compressor building work block work plastering/material shifting/ loading unloading strenthing work eva area | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Chiller Building + Pipe Rack G | NO | Yes | Yes | Piyush/Gopala krishna | Pintu/dahnuu | 35 | Sahnawaz | yes

## Y
To be filled by Contractor | [12 empty] | To be filled by Danone Rep.
Supplier name | Date | Shift (Day/Night) | Shift | Work Description | Type of permits Required (Pls. specify) | Job Location | Critical Activities | HIRA / JSA (Yes / No) : Number | Approved Method Statement (Yes / No) | Name of Contractor engineer responsible at site | Name of contractor safety officer responsible on site | Estimated Crew Size | Name of Area Owner / Sub-Owner | Verified by Area Owner (Y/N) | Remarks
Sample | 2026-06-15 | Day | A/B/C/G | Erection and welding of cooling tower piping at roof level on pipe rack using boom lift. Includes material shifting using Farana, alignment, fit-up, welding, and inspection. | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator 11Mtr | Work at height (>10M) using boom lift, hot work (welding), material lifting using Farana, working near roof edge | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | XX | XX
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Superheight 5) Heavy Lifting 6) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00
|  | Day |  | 1) Piperack Support fabrication and installation 2) Pipeline welding 3) Tanks Platform installation and fabrication 4) Fire hydrant pipeline dismantling and rerouting 5) Plaster Paint Putty Work 6) Material shifting manually and with farana(mobile crane) 7) Scaffolding erection and dismantling 8)Emergency Staircase and platform modification | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | 1) Piperack Support fabrication and installation 2) Super height using Boom lift 3) Fire hydrant pipeline dismantling and rerouting 4) Material shifting manually and with farana(mobile crane) | Yes | Yes | Wasi Ahmed | Sharukh Khan | 14 | Surender | YES | 09:00 to 18:00
|  | Night |  | 1) Piperack Support welding 2) Pipeline welding | 1) General Work 2) Hot work 3) Height Work 4) Loto | Evaporator terrace and cooling tower area | Welding Work | Yes | Yes | Ankush Saini | Hariom Kumar | 6 | Surender | YES | 18:00 to 06:00

## Esswin
Weekly Work Plan
Sr No. | Date | Day | Type of Job (Hot Work/ Excavation / Height Work > 6 ft or > 10M / HV Electrical work / Confined space / Line Breaking / Critical lifting / General /etc) | Area | Work Description | Critical Activities | Approved HIRA / JSA (Yes / No) | Approved Method Statement (Yes / No) | Name of Area Owner | Name of Task Owner | Contractor Name | Remarks
1 | 2026-06-29 | Monday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack | 1) Cable tray fixing at height using boom lift arrangement 2) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
2 | 2026-06-30 | Tuesday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site 3) Structure fabrication for cable laying/pulling at piperack | 1) Cable tray fixing at height using boom lift arrangement 2) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
3 | 2026-07-01 | Wednesday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site . 4)Cable tray support installation at PCC room area 5) Strip Jointing & fabrication. | 1) Cable tray fixing at height using boom lift arrangement 2) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
4 | 2026-07-02 | Thursday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site . 4)Cable tray support installation at PCC room area 5) Cable tray installation at PCC room area 6) Cable laying at Piperack. 5) Strip Jointing & fabrication. | 1) Cable tray fixing at height using boom lift arrangement 2) cable tray installation at PCC room area 3) Cable laying at Piperack. 4) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
5 | 2026-07-03 | Friday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site . 4)Cable tray support installation at PCC room area 5) Cable tray installation at PCC room area 6) Cable laying at Piperack. 5) Strip Jointing & fabrication. | 1) Cable tray fixing at height using boom lift arrangement 2) cable tray installation at PCC room area 3) Cable laying at Piperack. 4) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
6 | 2026-07-04 | Saturday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site . 4)Cable tray support installation at PCC room area 5) Cable tray installation at PCC room area 6) cable terminations 6) Cable laying at Piperack & New chiller area 5) Strip Jointing & fabrication. | 1) Cable tray fixing at height using boom lift arrangement 2) cable tray installation at PCC room area 3) Cable laying at Piperack. 4) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin
7 | 2026-07-05 | Saturday | Height Work//General Work | New Piperack Piperack & New Chiller building outside | 1) Cable tray shifting & Installation at Rack. 2) Earthing strip straightening & shifting at site . 4)Cable tray support installation at PCC room area 5) Cable tray installation at PCC room area 6) cable terminations 6) Cable laying at Piperack & New chiller area 5) Strip Jointing & fabrication. | 1) Cable tray fixing at height using boom lift arrangement 2) cable tray installation at PCC room area 3) Cable laying at Piperack. 4) Material shifting | yes | yes | Arun Chauhan | Danish | Esswin | Esswin

## Elect- Fluidline
Weekly Work Plan
Sr No. | Date | Day | Type of Job (Hot Work/ Excavation / Height Work > 6 ft or > 10M / HV Electrical work / Confined space / Line Breaking / Critical lifting / General /etc) | Area | Work Description | Critical Activities | Approved HIRA / JSA (Yes / No) | Approved Method Statement (Yes / No) | Name of Area Owner | Name of Task Owner | Contractor Name | Remarks
1 | 2026-06-29 | Monday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Equipment Tagging 3) MCC Reloaction at positioning 4) Cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) MCC shifting & Relocation | yes | yes | Pradip Sahu | Danish | Fluidline
2 | 2026-06-30 | Tuesday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) MCC Panel accessories fitting 3) Equipment Tagging 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) MCC accessories fitting | yes | yes | Pradip Sahu | Danish | Fluidline
3 | 2026-07-01 | Wednesday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) MCC Panel accessories fitting 3) Equipment Tagging 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) MCC panel accessories fitting. | Yes | yes | Pradip Sahu | Danish | Fluidline
4 | 2026-07-02 | Thursday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) Equipment Tagging 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. | Yes | yes | Pradip Sahu | Danish | Fluidline
5 | 2026-07-03 | Friday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) Equipment Tagging & termination 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) Cable terminations. | Yes | yes | Pradip Sahu | Danish | Fluidline
6 | 2026-07-04 | Saturday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) Equipment Tagging & termination 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) Cable terminations. | Yes | yes | Pradip Sahu | Danish | Fluidline
7 | 2026-07-05 | Sunday | Height Work//General Work | New Chiller Building | 1) Scaffoding dismantling & Erection work. 2) Cable laying 3) Equipment Tagging & termination 4) cable tray installation & fabrication | 1) Scaffolding dismantling & erection.. 2) Cable terminations. | Yes | yes | Pradip Sahu | Danish | Fluidline